## Folha1
TASK 3.1 : Transfer of moored fish aggregating devices (MFADs) from Guadeloupe to Azores and Madeira
Months
PLACES | TASKS | PARTNERS INVOLVED | DELIVERABLES | December 2017 | January 2018 | February | March | April | May | June | July | August | September | October | November | December | January 2018 | February | March | April
Azores | Contribution to Interim report | seaExpert | Interim Report
| Bibliographic review | seaExpert | Lessons learnt from successes and failures
| Fishing gear specifications | Guadeloupe » seaExpert | List of needs
| Shipowners contacts | seaExpert | MFAD setting reporting for Azores
| Experimental design | Guadeloupe | Models and detailed plans
| Contribution to Intermediary report | seaExpert | Intermediary Report
| Travelling | Guadeloupe
| MFAD building | seaExpert / Guadeloupe / local manufactores | MFAD setting reporting for Azores
| MFAD setting | seaExpert / Guadeloupe / local manufactores | MFAD setting reporting for Azores
| Permits and insurances | seaExpert | MFAD setting reporting for Azores
| Contact with the crew | seaExpert / Guadeloupe | MFAD setting reporting for Azores
| Monitoring / Data collection | seaExpert | MFAD monitoring reports including fishermen feedback and data
| Data processing | seaExpert | Deliverables of the data processed
| Data analysis | seaExpert | Deliverables of data analysed
| Report | seaExpert | Report
Madeira | Contribution to Interim report | seaExpert | Interim Report
| Bibliographic review | Madeira | Lessons learnt from successes and failures
| Fishing gear specifications | Guadeloupe » seaExpert / Madeira | List of needs
| Shipowners contacts | Madeira /seaExpert | MFAD setting reporting for Madeira
| Experimental design | Guadeloupe | Models and detailed plans
| Contribution to Intermediary report | seaExpert | Intermediary Report
| Travelling | Guadeloupe
| MFAD building | Madeira / seaExpert / Guadeloupe / local manufactores | MFAD setting reporting for Madeira
| MFAD setting | Madeira / seaExpert / Guadeloupe / local manufactores | MFAD setting reporting for Madeira
| Permits and insurances | seaExpert | MFAD setting reporting for Madeira
| Contact with the crew | Madeira / seaExpert / Guadeloupe | MFAD setting reporting for Madeira
| Monitoring / Data collection | Madeira / seaExpert | MFAD monitoring reports including fishermen feedback and data
| Data processing | Madeira / seaExpert | Deliverables of the data processed
| Data analysis | Madeira / seaExpert | Deliverables of data analysed
| Report | Madeira / seaExpert | Report